CoST – ETHIOPIA

(STANDARD TEMPLATE) PROJECT AND CONTRACT INFORMATION DISCLOSURE

FOR Construction of Lideta Branch Office Building

STANDARD TEMPLATE FOR CONTRACT AND PROJECT INFORMATION DISCLOSURE

| DISCLOSURE OF PROCUREMENT & CONTRCT INFORMATION (44 ITEMS) |
| --- |
| PHASE | ITEMS OF DISCLOSURE | CONSTRUCTION | DESIGN AND SUPERVISION |
| PROCUREMENT INFORMATION (30 ITEMS) | Date of disclosure | Megabit 30, 2011 E.C. |  |  |
|  | Contract title | Construction of Lideta Branch Office Building (GOV/NCB/W004/2008) |  |  |
|  | Location | Lideta Sub city, Addis Ababa |  |  |
|  | Procuring entity | AAWSA Water and Sanitation Development and Rehabilitation Project Office |  |  |
|  | Source for further information | Procurement team of the Project Office – Lideta Sub city, Wereda 04 around Lideta condominium on the left side of Lideta Menafesha |  |  |
|  | Date of procurement notice | March 02, 2016 |  |  |
|  | Floating period of the procurement notice | From March 03, 2016 to April 07, 2016 |  |  |
|  | Media used for procurement notice | The Ethiopian Herald |  |  |
|  | Method of procurement | National Competitive Bidding |  |  |
|  | Type of Procurement | Open national tender |  |  |
|  | Procurement procedure | Two envelop bid |  |  |
|  | Evaluation criteria | Public procurement proclamation of the Government of the Federal Democratic Republic of Ethiopia |  |  |
|  | DISCLOSURE OF PROCUREMENT & CONTRCT INFORMATION (44 ITEMS) |
|  | ITEMS OF DISCLOSURE | CONSTRUCTION | DESIGN | SUPERVISION |
|  | Type of contract & project delivery method | Admeasurement contract with bill of quantities |  |  |
|  | Type & Amount of bid security | ETB 435,000.00 (birr Four Hundred Thirty Five Thousand Only). The bid security shall be valid for 118 (one hundred eighteen) days from the date of bid opening date. The bid security shall be in the form of CPO or bank guarantee. |  |  |
|  | Content of any complaint lodged | None |  |  |
|  | Engineer’s estimate | ETB 88,191,473.39 (birr Eighty Eight Million One Hundred Ninety One Thousand Four Hundred Seventy Three & 39/100 Only) |  |  |
|  | Date of bid opening | April 07, 2016 |  |  |
|  | Number of bidders: Participated, rejected and declined to submit | Document procured - 58 Technical document submitted -18 Decline to submit - 40 |  |  |
|  | Awarded firm/contracting firm | Biyanko Building Contractor PLC. |  |  |
|  | Date of contract award | August 18, 2016 |  |  |
|  | Award price/original contract price | ETB 46,778,847.67 (birr Forty Six Million Seven Hundred Seventy Eight Thousand Eight Hundred Forty Seven & 67/100) without VAT |  |  |
|  | Unit Contract price (price/km, price/sq.meter) | Not applicable |  |  |
|  | Contract security type and amount | Performance Bond Guarantee (10% of Contract Amount) |  |  |
|  | Date of contract signing | August 18, 2016 |  |  |
|  | Contract scope | Construction of B+G+5 building |  |  |
|  | Description of contract & Contract components | B+G+5 branch office building construction, site work & fence |  |  |
|  | Contract administration entity | AAWSA Water and Sanitation Development and Rehabilitation Project Office |  |  |
|  | Contract duration | 540 days |  |  |
|  | Contract start date | November 06, 2016 |  |  |
|  | Intended completion date | April 30, 2018 |  |  |

| DISCLOSURE OF PROCUREMENT & CONTRCT INFORMATION (44 ITEMS) |
| --- |
|  | ITEMS OF DISCLOSURE | CONSTRUCTION | DESIGN | SUPERVISION |
|  | Contract status (ongoing, terminated, completed) | Completed |  |  |
| CONTRACT IMPLEMENTATION (14 ITEMS) | Completion date | February 18, 2019 |  |  |
|  | Changes to contract duration with Reason | 540 + 294 days due to additional works & rainy season |  |  |
|  | Amount of Liquidated Damage if applied (Penalty for delay) | Not applied |  |  |
|  | Contract price (Revised, projected, Actual) | ETB 46,778,847.67 (birr Forty Six Million Seven Hundred Seventy Eight Thousand Eight Hundred Forty Seven & 67/100) without VAT |  |  |
|  | Changes to contract price with reason | Due to: additional work & rainy season |  |  |
|  | Scope at completion | B+G+5 building, site work & fence |  |  |
|  | Changes to contract scope with reason | Fence was not included in the original contract |  |  |
|  | Total payment effected | ETB 46,029,609.22 (birr Forty Six Million Twenty Nine Thousand Six Hundred Nine & 22/100 Only) without VAT |  |  |
|  | warranty type and description | Performance bond guarantee (10% of the contract price in the form of an unconditional bank guarantee or conditional insurance bond from financial institution in Ethiopia. This contract security will be retained sixty (60) days from the date of the project completion) |  |  |
|  | Details of Termination if applied | Not applied |  |  |
|  | Safety Measures (accident & death) | None |  |  |
|  | Quality of work (very good, good, inferior, impossible to comment) | Very good |  |  |
|  | Disputed issues & Award details | No dispute |  |  |

| DISCLOSURE OF PROJECT INFORMATION (8/26 ITEMS) |
| --- |
| PROJECT INFORMATION AT COMPLETION (8 ITEMS) | Cost of the project at completion | ETB 50,458,481.05 (birr Fifty Million Four Hundred Fifty Eight Thousand Four Hundred Eighty One & 05/100 Only) without VAT |
|  | changes of project cost with reason | ETB 3,679,633.38 (birr Three Million Six Hundred Seventy Nine Thousand Six Hundred Thirty Three & 38/100 Only) without VAT |
|  | Project completion date (Revised, projected, actual) | February 18, 2019 |
|  | Actual duration for completing the whole project | 540 days |
|  | Changes of project duration with reason | Additional work & rainy season |
|  | Project Scope at completion | B+G+5 building and fence |
|  | Changes of project scope with reason | Fence work was not included in the original document |
|  | Reference to documents for disclosure upon request (reactive disclosure) | Bidding document for the construction of B+G+5 Lideta branch office building procurement of works (Procurement Ref. No. GOV/NCB/W004/2008), Contract agreement between Water and Sanitation Development & Rehabilitation Project Office (AAWSA) and Biyanko Building Contractor PLC for the construction of B+G+5 Lideta branch office building in Addis Ababa (Contract No. NCB / GOV /W005/2008) Volume I, The Ethiopian Herald 02 March 2016 |

| DISCLOSURE OF PROJECT INFORMATION (18/26 ITEMS) |
| --- |
| PRELIMINARY PROJECT INFORMATION (18 ITEMS) | Date of disclosure | Megabit 30, 2011 E.C. |
|  | Project owner | AAWSA Water and Sanitation Development and Rehabilitation Project Office |
|  | Project name | Construction of Lideta Branch Office |
|  | Sector, subsector | Water Study, Design and Construction Supervision Sub process |
|  | Source for further information | AAWSA Water and Sanitation Development & Rehabilitation Project Office – Lideta Sub city, Wereda 04 around Lideta condominium on the left side of Lideta Menafesha, tel: +251 116 676920 |
|  | Project Location | Lideta Sub city, Addis Ababa |
|  | Purpose | Branch office building for AAWSA |
|  | Project description | Branch office building construction |
|  | Original Project Scope | Construction of B+G+5 branch office building |
|  | Project Components | Civil Construction including building (architectural, structural, sanitary, electrical works), site work and fence |
|  | Environmental impact | No environmental impact |
|  | land & settlement impact | No land & settlement impact |
|  | Estimated budget of the project with breakdown of components | ETB 88,191,473.39 (birr Eighty Eight Million One Hundred Ninety One Thousand Four Hundred Seventy Three & 39/100 Only) |
|  | Funding sources | The Ethiopian Government |
|  | Project budget approval date | Not available |
|  | Project start date (planned, actual) | November 06, 2016 |
|  | Planned/ Original duration for completing the whole project | April 30, 2018 |
|  | Planned/Original cost of the project | ETB 46,778,847.67 (birr Forty Six Million Seven Hundred Seventy Eight Thousand Eight Hundred Forty Seven & 67/100) |